## Leadership Management
Deadline | Task | Initiative | Status of Task | Notes
Continuous | Finish Transition Documents for Fall/Spring FinApp | Continuity | In Progress
2020-04-25 | Meeting with SAC Leadership #1 (general) | Mending Fences | Completed | Agenda attached here
2020-04-29 | Attend SAC Meeting/Appeals | Mending Fences | Completed
2020-05-01 | Have first meeting of FinApp Leadership | Transition | Completed
2020-05-01 | Have first meeting with Aysha Dos | Transition | Completed
2020-05-01 | Complete Bi-Weekly Report #1 | Continuity | Completed
2020-05-10 | Set a clear schedule of Chair-VC Meetings | Transition | Completed
2020-05-11 | Meeting with CAB Chair Abhi Saravanan | Mending Fences | Completed | Agenda attached here
2020-05-13 | Send out Interest Forms and Ethics Disclosures | Transition | Completed
2020-05-15 | Complete Bi-Weekly Report #2 | Continuity | Completed
2020-05-16 | Have a transition meeting with Chair Arias | Transition | Completed
2020-05-16 | Have a meeting with former Chair Grande | Transition | Completed
2020-05-18 | Assign FinApp Portfolios | Transition | Completed
2020-05-18 | Have first FinApp Committee Meeting | Transition | Completed
2020-05-18 | Meeting with Leo Arnett about the Agora | GUSA Cooperation | Completed
2020-05-20 | Send out Policy Team Forms | Transition | Completed
2020-05-22 | Schedule Meeting with Leo Rassieur | GUSA Cooperation | Incomplete | extended to 6/22
2020-05-22 | Schedule Meeting with Pres. Ferretti, VP Badger | GUSA Cooperation | Completed
2020-05-25 | Mass Email to Advisory Boards/PartAs/PartBs | Mending Fences | Completed
2020-05-25 | Finalize Project Workflows | Transition | In Progress | *extended to 6/17*
2020-05-25 | Compile Ethics Disclosures and send to E&O | Transition | Completed
2020-05-28 | Introduce all liaisons to their groups | Transition | Completed
2020-05-29 | Schedule Meeting with CoS Rector | GUSA Cooperation | In progress | extended to 6/29
2020-05-29 | Complete Bi-Weekly Report #3 | Continuity | Completed
2020-06-01 | Finalize Summer Meeting Schedule | Transition | Completed | Biweekly
2020-06-01 | Schedule transition meeting with advisory boards | Transition | In progress | each liaison does this
2020-06-01 | Finalize Summer Syllabus Policy Sections | Transition | In progress | *extended to 6/17*
2020-06-10 | Finalize GUSA Internal Budget | Treasurer | Completed | approved in committee 6/10
2020-06-10 | Third FinApp Meeting | Management | Completed
2020-06-12 | Complete Bi-Weekly Report #4 | Continuity | Completed
2020-06-12 | Second Email to ABs and Groups | Communication | In Progress
2020-06-15 | Recap Email #1 | Management | Completed
2020-06-24 | Fourth FinApp Meeting | Management | Incomplete | Agenda 24 hours prior
2020-06-26 | Hold second set of check-in meetings | Management | Incomplete
2020-06-26 | Complete Bi-Weekly Report #5 | Continuity | Incomplete
2020-06-26 | Ensure Liaisons send First Monthly Email | Communication | Incomplete
2020-06-30 | Send Meeting Recap Email | Management | Incomplete
2020-07-08 | Fifth FinApp Meeting | Management | Incomplete
2020-07-10 | Complete Bi-Weekly Report #6 | Continuity | Incomplete
2020-07-10 | Third Email to ABs and Groups | Communication | Incomplete
2020-07-22 | Sixth FinApp Meeting | Management | Incomplete
2020-07-24 | Ensure Liaisons send Second Monthly Email | Communication | Incomplete
2020-07-24 | Complete Bi-Weekly Report #7 | Continuity | Incomplete
2020-08-05 | Seventh FinApp Meeting | Management | Incomplete
2020-08-07 | Complete Bi-Weekly Report #8 | Continuity | Incomplete
2020-08-07 | Fourth Email to ABs and Groups | Communication | Incomplete
2020-08-21 | Complete Bi-Weekly Report #9 | Continuity | Incomplete
2020-08-21 | Ensure Liaisons send Third Monthly Email | Communication | Incomplete

## in progress Leadership Reform
Initiative: FinApp Reforms
Treasurer Bylaws
2020-05-15 | Introduce Bylaw Reform Bill to Ways and Means | Completed
2020-06-07 | Have Bill Passed in Senate | In Progress | Initial delay from 5/24 to 6/7
Process Reforms
2020-06-22 | Liaison Memo Reviews | In Progress

## Team SEF
Initiative: the Student Empowerment Fund Project
Deadline | Assigned to | Task | Status of Task | Notes
Setting up Project Team
2020-05-20 | Bazail | Send out project interest forms | Completed | Due 05/22 at 5 PM EST
2020-05-23 | Bazail | Select Teams | Completed
2020-05-24 | Bazail | Appoint a Team Lead | Completed
2020-05-25 | Bazail | Schedule first team meeting | Completed | extended 6/12
2020-05-30 | Bazail | Complete first meeting, set roadmap, expectations, etc | In progress
2020-06-01 | Team Lead | Team Project Outline Completed | Incomplete | Add to syllabus; extended 6/17
Outreach to Administrators (First-Stage)
2020-05-22 | Bazail | Schedule meeting with Dr. Erika Cohen-Derr | Completed | Reference Juliana's e-mail
2020-05-29 | Bazail | Schedule meeting with Dustin Musser | Incomplete | Reference Juliana's e-mail
2020-05-29 | Bazail | Schedule meeting with VP Todd Olson | Incomplete | Reference Juliana's e-mail
Refining and Finalizing the SEF Proposal
2020-06-22 | Team | First readthrough | In progress
2020-08-06 | Team | First revisions to report | Incomplete | make separate version
2020-08-13 | Bazail/Dai/Lead | Hold meeting to go over revisions | Incomplete
2020-08-20 | Team | Second revisions to report | Incomplete
2020-08-27 | Team | Finalization | Incomplete
Lobbying and Coalition Building (Fall)

## Team Cultural Organizations Adv
Initiative: Cultural Organizations Policy Reform
Deadline | Assigned to | Task | Status | Notes
Setting up Project Team
2020-05-20 | Bazail | Send out project interest forms | Completed | Due 05/22 at 5 PM EST
2020-05-23 | Bazail | Select Teams | Completed
2020-05-24 | Bazail | Appoint a Team Lead | Completed
2020-05-25 | Bazail | Schedule first team meeting | Incomplete | postponed to 6/13
2020-05-30 | Everyone | Complete first meeting, set roadmap, expectations, etc | Incomplete
2020-06-01 | Kleier | Team Project Outline Completed | Incomplete | Add to syllabus; extended 6/17
Constructing an Effective Working Group
2020-06-29 | Bazail/Kleier | Write Act with rules governing this Working Group | Incomplete
2020-06-22 | Kleier | Send comms something to promote the team in GUSA Weekly | Incomplete
2020-06-20 | Kleier | Begin outreach to LLF, BLF, APILF, and other campus groups | Incomplete | Meet with leaders, try to get it on weekly newsletters
2020-06-20 | Bazail/Kleier | Begin holding regular meetings with Sung and Saravanan | Incomplete | Sung- Race/Inclusivity PC, Saravanan- Student Orgs
2020-06-20 | Kleier | Begin holding regular meetings with Arnett | Incomplete | Arnett- oversees Agora and its infrastructure
2020-06-20 | Kleier | Set and begin holding meetings with Moreland | Incomplete | Moreland- as GUSA Exec Liaison

## Team SAF Reform
Initiative: Student Activity Fee Reform
Deadline | Assigned to | Task | Status of Task | Notes
Setting up Project Team
2020-05-20 | Bazail | Send out project interest forms | Completed
2020-05-23 | Bazail | Select Teams | Completed
2020-05-24 | Bazail | Appoint a Team Lead | Completed
2020-05-25 | Bazail | Schedule first team meeting | Completed
2020-05-30 | All | Complete first meeting, set roadmap, expectations, etc | Completed
2020-06-01 | Team Lead | Team Project Outline Completed | In progress | Add to syllabus; extended 6/26
Preliminary Stakeholder Outreach
2020-04-25 | Bazail/Dai | Meeting with SAC Leadership #1 (general) | Completed | Agenda attached here
2020-05-11 | Bazail/Dai | Meeting with CAB Chair Abhi Saravanan | Completed | Agenda attached here
2020-06-30 | Team | Look at CRSC Data from Club Survey | In progress
Report Writing
2020-06-26 | All | Report Outline Due | In progress
2020-08-06 | All | First Draft of Report | Incomplete
2020-08-13 | All | Prepare Presentation to Committee | Incomplete
2020-09-07 | All | Finalization of Report | Incomplete
GEMS/GUPD/CETS Subteam